## Cover
ePricing Service — Enterprise Upgrade Trainee Work & Learning Tracker
Trainee Name: | [Your Name] | Department: | Technology / Digital Onboarding
Mentor: | Senior DevOps Engineer | Start Date: | 10-Jul-2026
Project: | ePricing Service — Local to Enterprise-Grade Infrastructure | Status: | In Progress - Core Observability Polish & Docs
Tech Stack: | Spring Boot 3 · Java 21 · Dapr · OpenTelemetry · Prometheus · Loki · Tempo · Grafana · Dynatrace · Kubernetes · PostgreSQL · SonarQube · GitHub Actions · Docker | Updated Date: | 12-Aug-2026
Work Hours: | 09:30 AM – 06:00 PM | Weekends: | Saturday & Sunday OFF
Total Phases: | P0 Foundation (IN REVISION) + P1-A Monitoring (90%) + Enterprise Phases P1-B to P6 | Est. Completion: | Nov-2026
PROJECT PHASE OVERVIEW
Phase | Name | Confirmed Tech Stack | Duration | Status
P0 | Foundation & Revision | Java 21 · Spring Boot 3 · Spring Core/DI · Docker · Maven · IntelliJ | Week 1 + Ongoing | IN REVISION (65%)
P1-A | Core Observability Stack | Prometheus · Micrometer · Grafana · PromQL · Loki · OpenTelemetry · Tempo · Dynatrace | Weeks 2–7 (13-Jul–20-Aug) | IN PROGRESS (90%)
P1-B | Kubernetes Fundamentals | Kubernetes · kubectl · minikube · HPA · ConfigMap · Secret · Ingress | Weeks 7–9 (21-Aug–11-Sep) | NOT STARTED
P2 | Production Database | PostgreSQL 16 · Flyway · K8s StatefulSet · PersistentVolumeClaim | Weeks 10–11 (14-Sep–25-Sep) | NOT STARTED
P3 | Enterprise Security | Spring Security 6 · OAuth2/JWT · K8s Secrets · TLS/Ingress HTTPS | Weeks 12–13 (28-Sep–09-Oct) | NOT STARTED
P4 | CI/CD Pipeline | GitHub Actions · Docker Build · SonarQube · K8s Rolling Deploy | Weeks 14–15 (12-Oct–23-Oct) | NOT STARTED
P5 | Observability Scale-Up | Prometheus K8s SD · Grafana Alerting · Loki 90-day · OTel Sampling · Dynatrace OTLP | Weeks 16–17 (26-Oct–06-Nov) | NOT STARTED
P6 | K8s Infra Utilization Dashboard | Prometheus Node Exporter · kube-state-metrics · Container/Node/Pod metrics · Grafana · Dapr observability | Weeks 18–19 (09-Nov–20-Nov) | NOT STARTED

## Learning Tracker
Week | Day / Period | Planned Hrs | Date Range | Priority | Phase / Module | Learning Topic | Sub-topic / Task | Office Work / Context | Completed? | Actual Duration | Status | Notes / Key Learnings | Next Action
PHASE 0 — Foundation & Environment Setup [IN REVISION — Spring Boot Internals + Spring Core/DI]
Week 1 | Session 1-2 | 7.5h | 10-Jul-2026 | P0 | P0 — Foundation | Environment Setup | Install Java 21 (Temurin), Maven 3.9, IntelliJ IDEA, Postman; project kickoff with mentor; run first mvn clean install; explore project folder structure | Project kickoff + mentor intro | Yes | 7.5h | Completed | Project scope: 13 monitoring targets; Java 21 LTS + Virtual Threads concept noted; JAVA_HOME had to be set manually | Begin Spring Boot revision
Ongoing | Revision | 1-2h/day | Jul – Aug 2026 | P0 | P0 — Foundation | Spring Boot 3 Internals | Revise: @SpringBootApplication, @EnableAutoConfiguration, @Conditional mechanism, spring.factories / AutoConfiguration.imports; Bean lifecycle (instantiation, injection, destruction); ApplicationContext vs BeanFactory; @ConfigurationProperties; Spring Profiles (@Profile, spring.profiles.active); Actuator endpoint internals | Parallel to main project | No | — | In Revision | Surface-level usage done during P1-A; auto-config mechanism, @Conditional chains and bean lifecycle not yet fully understood; spring.factories mechanism unclear | Trace bean creation in debugger; read @SpringBootApplication source
Ongoing | Revision | 1-2h/day | Aug – Sep 2026 | P0 | P0 — Foundation | Spring Core — DI & AOP | Revise: @Autowired field vs constructor vs setter injection; @Primary vs @Qualifier; circular dependency resolution; @Aspect, @Around, @Before, @After, Pointcut expressions; JDK dynamic proxy vs CGLIB proxy; Spring MVC DispatcherServlet request lifecycle; @ControllerAdvice + @ExceptionHandler | Parallel to project; AOP needed for P3 @AuditLog | No | — | In Revision | @Autowired used in project but proxy mechanism and AOP internals not studied; DispatcherServlet lifecycle not traced; @AuditLog task needs AOP prerequisite | Write @Aspect demo; draw DispatcherServlet flow diagram
PHASE 1-A — Core Observability Stack (Weeks 2–7 ¦ 13-Jul – 20-Aug-2026)
Week 2 | Mon-Fri | 37.5h | 13–17 Jul 2026 | P0 | P1-A — Observability | Docker + Spring Boot (Surface) | Install Docker Desktop (WSL2); run mvn clean install; test APIs via Postman; read PricingController + PricingService; study Prometheus pull model + observability 3 pillars (metrics/logs/traces) | Daily standup + mentor 1:1 | Yes | 37.5h | Completed | Docker required BIOS Hyper-V+WSL2; Actuator on port 8081; pull vs push model understood. NOTE: Spring Boot used surface-level only — internals need revision in P0 track | Configure micrometer-registry-prometheus
Week 3 | Mon-Fri | 37.5h | 20–24 Jul 2026 | P0 | P1-A — Observability | Prometheus + Grafana Setup | Add micrometer-registry-prometheus to pom.xml; write prometheus.yml scrape config; run Prometheus in Docker Compose; add Grafana datasource; create first dashboard panels (CPU/threads); study PromQL rate() | Daily standup + mentor 1:1 | Yes | 37.5h | Completed | Fixed scrape port 8080→8081 (target was DOWN); Grafana auto-provisioned via datasources YAML; rate() converts counter to per-second rate; sum() by() = GROUP BY SQL | Create JVM + HTTP + DB dashboard panels
Week 4 | Mon-Fri | 37.5h | 27–31 Jul 2026 | P0 | P1-A — Observability | Full Grafana Dashboard + Traffic Generator | Create JVM Heap/NonHeap/GC Pause P99 panels; P95/P99 latency panels; error rate panel; app health Stat panel; implement traffic generator shell script (HOME_LOAN/AUTO_LOAN/PERSONAL_LOAN + error scenarios); fix panel ID conflicts; add row sections | Daily standup + mentor 1:1 | Yes | 37.5h | Completed | le label must be in sum() by() for histogram_quantile(); error rate uses =~5.. regex; traffic generator sends all 3 loan types + 400/500 errors; panel ID conflicts resolved | Add panel descriptions; full E2E test; verify Prometheus alert rules
Week 5 | Mon-Fri | 37.5h | 03–07 Aug 2026 | P0 | P1-A — Observability | Panel Descriptions + Alert Rule Testing | Add panel descriptions to all 15 panels; export provisioned dashboard JSON; test Prometheus alert rules in application-alerts.yml (inactive→pending→firing); run mixed load via traffic generator; verify metric scrape frequency (15s) | Daily standup + mentor 1:1 | Yes | 37.5h | Completed | Panel descriptions explain what each metric measures; alert rule evaluation interval confirmed; error rate alert triggers properly when 5xx errors injected | Fine-tune thresholds + start documentation guides
Week 6 | Mon-Fri | 37.5h | 10–14 Aug 2026 | P0 | P1-A — Observability | Threshold Tuning + Initial Guides [CURRENT] | Adjust CPU threshold from 80% to 75%; fix Grafana legend formatting (clean legend names vs raw PromQL output); draft ARCHITECTURE_EXPLAINED.md and SIMPLE_OBSERVABILITY_GUIDE.md; test container restart persistence | Daily standup + mentor 1:1 | Yes | 37.5h | In Progress | Legend formatting cleaned up; Prometheus data volume stays intact across container restart; documentation drafts reviewed with team | Complete documentation polish & mentor sign-off
Week 7 | Mon-Thu | 30.0h | 17–20 Aug 2026 | P0 | P1-A — Observability | Mentor Review + Doc Polish + Sign-Off | Review monitoring setup with mentor; implement mentor feedback (adjust alert 'for' duration from 1m to 2m to prevent false spikes); finalize README.md setup steps; test clean import on fresh workspace; formal Phase 1-A sign-off meeting | Mentor review + demo session | No | — | Planned | Mentor sign-off achieved; all 15 panels verified; setup steps tested on clean environment; ready for K8s phase | Begin Phase 1-B Kubernetes on 21-Aug
PHASE 1-B — Kubernetes Fundamentals (Weeks 7–9 ¦ 21-Aug – 11-Sep-2026) [NOT STARTED]
Week 7-8 | Fri-Fri | 45.0h | 21–28 Aug 2026 | P0 | P1-B — Kubernetes | K8s Concepts + Local Setup | Study: Node, Pod, Deployment, Service, ConfigMap, Secret, Namespace; install kubectl + minikube; deploy Hello World pod; create epricing namespace + ServiceAccount + Role; write ConfigMap for env vars + Secret for DB credentials; mount in Pod spec | LD-01, LD-02, LD-03, LD-04 | No | — | Not Started | Understand Node→Pod→Container hierarchy; kubectl get pods -n epricing; cross-namespace access; ConfigMap+Secret env injection | Install minikube + write Deployment manifest
Week 8-9 | Mon-Fri | 37.5h | 31-Aug–04-Sep 2026 | P0 | P1-B — Kubernetes | Deployment + Service + Ingress | Write Deployment manifest (replicas:3) with liveness probe (/actuator/health) + readiness probe; write ClusterIP Service; configure Nginx Ingress exposing /api/v1; test with curl via Ingress host | LD-05, LD-06 | No | — | Planned | 3 pods Running; kubectl rollout status complete; curl http://epricing.local/api/v1/health returns 200 OK | Configure HPA + resource limits
Week 9 | Mon-Fri | 37.5h | 07–11 Sep 2026 | P0 | P1-B — Kubernetes | HPA + Resource Limits | Configure HPA (min:2 max:10 CPU>70%); set Pod requests (256Mi/250m) and limits (512Mi/1000m); run load test; observe automatic scale-up; verify OOMKilled does not occur under normal load | LD-07, LD-08 | No | — | Planned | kubectl get hpa shows CPU Targets increasing; pod count scales from 2 to higher under load; limits prevent OOMKilled | Begin PostgreSQL phase
PHASE 2 — Production Database (PostgreSQL + Flyway) (Weeks 10–11 ¦ 14-Sep – 25-Sep-2026)
Week 10 | Mon-Fri | 37.5h | 14–18 Sep 2026 | P0 | P2 — Database | PostgreSQL K8s StatefulSet | Deploy PostgreSQL 16 StatefulSet with PersistentVolumeClaim in K8s; connect psql CLI; configure Spring Boot prod datasource in application.yml; remove H2 dependency from pom.xml | LD-09, LD-10 | No | — | Planned | StatefulSet gives stable Pod identity; PVC preserves data across Pod restarts; /actuator/health shows db UP; POST /pricing saves to PostgreSQL | Add Flyway migration
Week 11 | Mon-Fri | 37.5h | 21–25 Sep 2026 | P0 | P2 — Database | Flyway Migration + Backup | Write Flyway V1__init.sql migration script creating pricing_requests table; add Flyway to pom.xml; verify migration runs on startup; document pg_dump daily backup strategy | LD-11, LD-12 | No | — | Planned | Flyway: Successfully applied 1 migration appears in startup logs; pg_dump generates .sql backup file; restore from backup works in test environment | Begin Security phase

## Daily Timesheet
Date | Day | Start Time | End Time | Activity / Task | Duration | Type | Status | Remarks / Key Learning
WEEK 1 — 10 Jul 2026 (Fri ¦ Day 1) Phase 0 — Foundation
10-Jul-2026 | Friday | 09:30 | 10:30 | Project kickoff with mentor — scope, 13 monitoring targets, tech stack explained | 1h 00m | [MEETING] | Completed | 13 metrics listed; ePricing monitoring project scope understood
10-Jul-2026 | Friday | 10:30 | 11:30 | Read README.md + pom.xml; explore Spring Boot project folder structure | 1h 00m | Work | Completed | Spring Boot 3.3.4 + Java 21 dependencies noted; package layout: controller/service/metrics/config
10-Jul-2026 | Friday | 11:30 | 13:00 | Install Java 21 (Temurin); set JAVA_HOME; verify java -version | 1h 30m | Work | Completed | Java 21.0.4 installed; JAVA_HOME set manually (not auto-set by installer)
10-Jul-2026 | Friday | 13:00 | 14:00 | Lunch Break | 1h 00m | Break | — | —
10-Jul-2026 | Friday | 14:00 | 15:30 | Install Maven 3.9; configure PATH; verify mvn -version | 1h 30m | Work | Completed | Maven 3.9.5 installed; settings.xml reviewed
10-Jul-2026 | Friday | 15:30 | 17:00 | Install IntelliJ IDEA Community; import project; install Postman | 1h 30m | Work | Completed | Project opened; all source files visible; GET/POST /pricing templates in Postman
10-Jul-2026 | Friday | 17:00 | 18:00 | First mvn clean install — download dependencies; review build output | 1h 00m | Work | Completed | Build took 9 min; fat JAR created in target/; all dependencies resolved
11-Jul-2026 | Saturday | — | — | Weekend — No Work | — | OFF | — | —
12-Jul-2026 | Sunday | — | — | Weekend — No Work | — | OFF | — | —
WEEK 2 — 13–17 Jul 2026 Phase 1-A — Docker + Observability Architecture Study
13-Jul-2026 | Monday | 09:30 | 09:45 | Daily standup — Day 1 progress; plan Docker install | 0h 15m | [MEETING] | Completed | Mentor: prioritise Docker Desktop
13-Jul-2026 | Monday | 09:45 | 10:30 | Week 2 planning with mentor | 0h 45m | [MEETING] | Completed | Week 2 goal: complete env setup + begin architecture study
13-Jul-2026 | Monday | 10:30 | 12:00 | Install Docker Desktop; troubleshoot WSL2 BIOS issue | 1h 30m | Work | Completed | Root cause: Hyper-V + WSL2 disabled in BIOS; enabled and rebooted; Docker running
13-Jul-2026 | Monday | 12:00 | 13:00 | Run mvn clean install; test app; create Postman collection | 1h 00m | Work | Completed | App starts on 8080; 201 Created for POST /pricing
13-Jul-2026 | Monday | 13:00 | 14:00 | Lunch Break | 1h 00m | Break | — | —
13-Jul-2026 | Monday | 14:00 | 18:00 | Read PricingController + PricingService; study Prometheus pull model; observability 3 pillars | 4h 00m | Study | Completed | Thin controller pattern; Counter.increment() + Timer.record() in service; Prometheus PULLS not pushes
14-Jul-2026 | Tuesday | 09:30 | 09:45 | Daily standup | 0h 15m | [MEETING] | Completed | —
14-Jul-2026 | Tuesday | 09:45 | 13:00 | Study OTel spans/traces/OTLP/context propagation; Micrometer metric types (Counter/Timer/Gauge) | 3h 15m | Study | Completed | traceId links all spans; Counter only up; Timer records count+duration; Gauge can go down
14-Jul-2026 | Tuesday | 13:00 | 14:00 | Lunch Break | 1h 00m | Break | — | —
14-Jul-2026 | Tuesday | 14:00 | 18:00 | Study Loki + Tempo + Grafana architecture; Docker networking; actuator endpoints | 4h 00m | Study | Completed | Grafana stores nothing; Loki stores logs; Tempo stores traces; containers reach each other by service name
15-Jul-2026 | Wednesday | 09:30 | 09:45 | Daily standup | 0h 15m | [MEETING] | Completed | —
15-Jul-2026 | Wednesday | 09:45 | 13:00 | Read Spring Boot Actuator docs; configure management.server.port=8081; expose health/metrics/prometheus | 3h 15m | Work | Completed | /actuator/prometheus returning Prometheus text format on port 8081
15-Jul-2026 | Wednesday | 13:00 | 14:00 | Lunch Break | 1h 00m | Break | — | —
15-Jul-2026 | Wednesday | 14:00 | 18:00 | Add micrometer-registry-prometheus to pom.xml; verify /actuator/prometheus returns 800+ metric lines | 4h 00m | Work | Completed | pricing_requests_total{product_type=HOME_LOAN status=SUCCESS} incremented per API call
16-Jul-2026 | Thursday | 09:30 | 09:45 | Daily standup | 0h 15m | [MEETING] | Completed | —
16-Jul-2026 | Thursday | 09:45 | 13:00 | Write prometheus.yml; add Prometheus + Loki + Tempo to docker-compose.yml; run docker-compose up | 3h 15m | Work | Completed | prometheus.yml scrape config; all services in docker-compose; Prometheus target initially DOWN
16-Jul-2026 | Thursday | 13:00 | 14:00 | Lunch Break | 1h 00m | Break | — | —
16-Jul-2026 | Thursday | 14:00 | 18:00 | Debug Prometheus target DOWN; fix port 8080→8081; run first PromQL queries | 4h 00m | Work | Completed | Target shows UP after port fix; up{job=epricing-service}=1; rate() function tested
17-Jul-2026 | Friday | 09:30 | 09:45 | Daily standup | 0h 15m | [MEETING] | Completed | —
17-Jul-2026 | Friday | 09:45 | 13:00 | Add Grafana to docker-compose; add Prometheus+Loki+Tempo datasources; configure provisioning YAML | 3h 15m | Work | Completed | All 3 datasources auto-provisioned via grafana/provisioning/datasources/; no manual setup needed
17-Jul-2026 | Friday | 13:00 | 14:00 | Lunch Break | 1h 00m | Break | — | —
17-Jul-2026 | Friday | 14:00 | 15:45 | Create first dashboard panels: CPU usage + thread count | 1h 45m | Work | Completed | stat panels with 80% CPU threshold colouring
17-Jul-2026 | Friday | 15:45 | 17:15 | Mentor 1:1 — Week 2 review; Prometheus + Grafana setup approved | 1h 30m | [MEETING] | Completed | Mentor approved setup; advised to add descriptions to all panels
17-Jul-2026 | Friday | 17:15 | 18:00 | Update task tracker AT-01 to AT-06; write Week 2 summary | 0h 45m | Work | Completed | Tasks updated; summary written
18-Jul-2026 | Saturday | — | — | Weekend — No Work | — | OFF | — | —
19-Jul-2026 | Sunday | — | — | Weekend — No Work | — | OFF | — | —
WEEK 3 — 20–24 Jul 2026 Phase 1-A — Full Dashboard Build
20-Jul-2026 | Monday | 09:30 | 09:45 | Daily standup + Week 3 planning with mentor | 1h 00m | [MEETING] | Completed | Week 3 goal: full dashboard panels + traffic generator
20-Jul-2026 | Monday | 09:45 | 13:00 | Practice PromQL: rate()/sum() by()/increase()/histogram_quantile()/label filters | 3h 15m | Study | Completed | sum() by(label) = GROUP BY SQL; le label must be preserved in by() for histogram_quantile
20-Jul-2026 | Monday | 13:00 | 14:00 | Lunch Break | 1h 00m | Break | — | —
20-Jul-2026 | Monday | 14:00 | 18:00 | Create JVM Heap + Non-Heap + GC Pause P99 panels | 4h 00m | Work | Completed | histogram_quantile(0.99) for GC; non-heap holds class metadata not objects; used _bucket suffix
21-Jul-2026 | Tuesday | 09:30 | 09:45 | Daily standup | 0h 15m | [MEETING] | Completed | —
21-Jul-2026 | Tuesday | 09:45 | 13:00 | Create HTTP request rate + P95 latency + P99 latency + error rate panels | 3h 15m | Work | Completed | NaN fixed by adding le to sum() by(); =~5.. regex matches all 5xx codes
21-Jul-2026 | Tuesday | 13:00 | 14:00 | Lunch Break | 1h 00m | Break | — | —
21-Jul-2026 | Tuesday | 14:00 | 18:00 | Create application health Stat panel; implement traffic generator shell script | 4h 00m | Work | Completed | up{job=epricing-service} Stat panel; traffic generator sends HOME_LOAN/AUTO_LOAN + error scenarios
22-Jul-2026 | Wednesday | 09:30 | 09:45 | Daily standup | 0h 15m | [MEETING] | Completed | —
22-Jul-2026 | Wednesday | 09:45 | 13:00 | Fix panel ID conflicts; add row sections (JVM/HTTP/Health); export dashboard JSON for provisioning | 3h 15m | Work | Completed | All 15+ panels updating live; panel ID conflicts resolved; dashboard auto-loads on compose up
22-Jul-2026 | Wednesday | 13:00 | 14:00 | Lunch Break | 1h 00m | Break | — | —
22-Jul-2026 | Wednesday | 14:00 | 18:00 | Review prometheus/alerts/application-alerts.yml; test alert rules (inactive→pending→firing) | 4h 00m | Work | Completed | Alert fires correctly after 'for' duration; 'for' clause prevents false alerts from brief spikes
23-Jul-2026 | Thursday | 09:30 | 09:45 | Daily standup | 0h 15m | [MEETING] | Completed | —
23-Jul-2026 | Thursday | 09:45 | 13:00 | Full E2E test: docker-compose up --build; verify all services start; all 4 scrape targets UP | 3h 15m | Work | Completed | All 6 services started; epricing/prometheus/otel-collector/otel-metrics all UP in targets page
23-Jul-2026 | Thursday | 13:00 | 14:00 | Lunch Break | 1h 00m | Break | — | —
23-Jul-2026 | Thursday | 14:00 | 18:00 | Run traffic generator; verify all 15+ Grafana panels update in real time; document test results | 4h 00m | Work | Completed | 12/15 panels verified; 3 remaining (GC/JVM under load); testing log maintained
24-Jul-2026 | Friday | 09:30 | 09:45 | Daily standup | 0h 15m | [MEETING] | Completed | —
24-Jul-2026 | Friday | 09:45 | 13:00 | Complete panel descriptions for all 15 dashboard panels; add descriptions to JSON | 3h 15m | Work | Completed | Every panel has description explaining what the metric measures and why it matters
24-Jul-2026 | Friday | 13:00 | 14:00 | Lunch Break | 1h 00m | Break | — | —
24-Jul-2026 | Friday | 14:00 | 15:30 | Test GC + JVM memory panels under sustained load from traffic generator | 1h 30m | Work | Completed | All 15 panels verified; GC pause P99 shows sub-ms values at normal load
24-Jul-2026 | Friday | 15:30 | 17:15 | Mentor 1:1 — Week 3 review; dashboard approved | 1h 45m | [MEETING] | Completed | Mentor approved dashboard; Phase 1-A monitoring complete; begin K8s Phase 1-B
24-Jul-2026 | Friday | 17:15 | 18:00 | Update task tracker AT-07 to AT-16; begin Phase 1-B K8s planning | 0h 45m | Work | Completed | AT-16 documentation 60% complete; K8s study plan created
25-Jul-2026 | Saturday | — | — | Weekend — No Work | — | OFF | — | —
26-Jul-2026 | Sunday | — | — | Weekend — No Work | — | OFF | — | —
WEEK 4 — 27–31 Jul 2026 Phase 1-A — Panel Formatting & PromQL Refinement
27-Jul-2026 | Monday | 09:30 | 13:00 | Refine HTTP P95/P99 PromQL queries; fix raw query text in legend outputs | 3h 30m | Work | Completed | Clean legends like 'P95 Latency' instead of raw PromQL string
27-Jul-2026 | Monday | 13:00 | 14:00 | Lunch Break | 1h 00m | Break | — | —
27-Jul-2026 | Monday | 14:00 | 18:00 | Test 500 error rate panel under simulated 50xx error injection from traffic generator | 4h 00m | Work | Completed | Error rate panel updated dynamically; verified regex =~5..
28-Jul-2026 | Tuesday | 09:30 | 13:00 | Review JVM GC pause buckets; compare GC duration across G1GC vs Parallel GC notes | 3h 30m | Study | Completed | Understood GC pause metrics from Micrometer jvm_gc_pause_seconds
28-Jul-2026 | Tuesday | 13:00 | 14:00 | Lunch Break | 1h 00m | Break | — | —
28-Jul-2026 | Tuesday | 14:00 | 18:00 | Organize Grafana dashboard into collapsable row sections (JVM / HTTP / System / Health) | 4h 00m | Work | Completed | Row sections added; clean visual hierarchy in Grafana UI
29-Jul-2026 | Wednesday | 09:30 | 13:00 | Test custom metrics exposure: pricing_requests_total by loan type (HOME/AUTO/PERSONAL) | 3h 30m | Work | Completed | Counter increments verified per loan type in Prometheus UI
29-Jul-2026 | Wednesday | 13:00 | 14:00 | Lunch Break | 1h 00m | Break | — | —
29-Jul-2026 | Wednesday | 14:00 | 18:00 | Test Loki log scraping; verify log level formatting (INFO/WARN/ERROR) in Grafana Explore | 4h 00m | Work | Completed | Logs queryable in Loki using {app='epricing-service'}
30-Jul-2026 | Thursday | 09:30 | 13:00 | Test OpenTelemetry context propagation; trace request from Controller through Service layer | 3h 30m | Work | Completed | traceId appears in logs and Tempo trace spans
30-Jul-2026 | Thursday | 13:00 | 14:00 | Lunch Break | 1h 00m | Break | — | —
30-Jul-2026 | Thursday | 14:00 | 18:00 | Draft architecture flow diagram for README.md: Spring Boot → Micrometer → Prometheus → Grafana | 4h 00m | Work | Completed | Flow diagram drafted in Markdown
31-Jul-2026 | Friday | 09:30 | 13:00 | Weekly progress review with mentor; share current dashboard state | 3h 30m | [MEETING] | Completed | Mentor suggested fine-tuning alert rule threshold to 5% error rate
31-Jul-2026 | Friday | 13:00 | 14:00 | Lunch Break | 1h 00m | Break | — | —
31-Jul-2026 | Friday | 14:00 | 18:00 | Update application-alerts.yml per mentor advice; re-test alert evaluation | 4h 00m | Work | Completed | Alert threshold set to 5% for 2m duration
01-Aug-2026 | Saturday | — | — | Weekend — No Work | — | OFF | — | —
02-Aug-2026 | Sunday | — | — | Weekend — No Work | — | OFF | — | —
WEEK 5 — 03–07 Aug 2026 Phase 1-A — Traffic Generator Load Test & Alert Verification
03-Aug-2026 | Monday | 09:30 | 13:00 | Run traffic generator script for 2 hours continuous load; monitor CPU/RAM stability | 3h 30m | Work | Completed | CPU stayed under 40%; heap memory auto-reclaimed by GC
03-Aug-2026 | Monday | 13:00 | 14:00 | Lunch Break | 1h 00m | Break | — | —
03-Aug-2026 | Monday | 14:00 | 18:00 | Verify Prometheus metric retention in volume mount; test restart of Prometheus container | 4h 00m | Work | Completed | Metric history persisted after docker-compose restart
04-Aug-2026 | Tuesday | 09:30 | 13:00 | Test Tempo trace visualization; verify span duration matches Spring Boot Timer metrics | 3h 30m | Work | Completed | Tempo trace span timing matched Micrometer pricing_duration timer
04-Aug-2026 | Tuesday | 13:00 | 14:00 | Lunch Break | 1h 00m | Break | — | —
04-Aug-2026 | Tuesday | 14:00 | 18:00 | Draft SIMPLE_OBSERVABILITY_GUIDE.md — write metric, log, and trace explanations | 4h 00m | Work | Completed | Draft created in docs/ directory
05-Aug-2026 | Wednesday | 09:30 | 13:00 | Test error injection scenario in traffic generator; verify HighErrorRate alert status | 3h 30m | Work | Completed | Alert transitioned: Inactive → Pending → Firing
05-Aug-2026 | Wednesday | 13:00 | 14:00 | Lunch Break | 1h 00m | Break | — | —
05-Aug-2026 | Wednesday | 14:00 | 18:00 | Export provisioned dashboard JSON file to grafana/provisioning/dashboards/ | 4h 00m | Work | Completed | Dashboard auto-loads on fresh docker-compose up
06-Aug-2026 | Thursday | 09:30 | 13:00 | Add panel descriptions for all 15 panels in Grafana edit mode | 3h 30m | Work | Completed | Info icon appears on each panel with clear description
06-Aug-2026 | Thursday | 13:00 | 14:00 | Lunch Break | 1h 00m | Break | — | —
06-Aug-2026 | Thursday | 14:00 | 18:00 | Write section on PromQL query examples in ARCHITECTURE_EXPLAINED.md | 4h 00m | Work | Completed | Added 10 PromQL query snippets with line-by-line explanations
07-Aug-2026 | Friday | 09:30 | 13:00 | Mentor 1:1 check-in; demo full LGTM monitoring stack | 3h 30m | [MEETING] | Completed | Mentor approved stack; requested minor legend adjustments for HTTP latency
07-Aug-2026 | Friday | 13:00 | 14:00 | Lunch Break | 1h 00m | Break | — | —
07-Aug-2026 | Friday | 14:00 | 18:00 | Make requested legend adjustments; re-export dashboard JSON | 4h 00m | Work | Completed | Legend now shows clean HTTP method + status label
08-Aug-2026 | Saturday | — | — | Weekend — No Work | — | OFF | — | —
09-Aug-2026 | Sunday | — | — | Weekend — No Work | — | OFF | — | —
WEEK 6 — 10–14 Aug 2026 Phase 1-A — Documentation & Stack Sanity Check [CURRENT]
10-Aug-2026 | Monday | 09:30 | 13:00 | Review full monitoring setup; check all 6 Docker services in docker-compose | 3h 30m | Work | Completed | epricing-service, prometheus, grafana, loki, tempo, otel-collector all healthy
10-Aug-2026 | Monday | 13:00 | 14:00 | Lunch Break | 1h 00m | Break | — | —
10-Aug-2026 | Monday | 14:00 | 18:00 | Update docs/README.md with quickstart commands and port table | 4h 00m | Work | Completed | Table of ports (8080 app, 8081 actuator, 9090 prom, 3000 grafana) added
11-Aug-2026 | Tuesday | 09:30 | 13:00 | Test clean workspace build: docker-compose down -v && docker-compose up --build | 3h 30m | Work | Completed | All datasources and dashboards auto-loaded without manual steps
11-Aug-2026 | Tuesday | 13:00 | 14:00 | Lunch Break | 1h 00m | Break | — | —
11-Aug-2026 | Tuesday | 14:00 | 18:00 | Draft interview preparation notes on Observability 3 Pillars for mentor review | 4h 00m | Work | Completed | Drafted Q&A notes on Prometheus pull model vs Pushgateway
12-Aug-2026 | Wednesday | 09:30 | 13:00 | [TODAY] Confirmed tech stack alignment with mentor; updated timesheet structure | 3h 30m | Work | Completed | Removed unneeded tools; confirmed Dynatrace + Dapr + K8s + PostgreSQL + SonarQube
12-Aug-2026 | Wednesday | 13:00 | 14:00 | Lunch Break | 1h 00m | Break | — | —
12-Aug-2026 | Wednesday | 14:00 | 18:00 | Update task trackers and documentation to reflect 20-Aug Phase 1-A end date | 4h 00m | Work | In Progress | Phase 1-A extended to 20-Aug for thorough doc polish and mentor sign-off
13-Aug-2026 | Thursday | 09:30 | 13:00 | Build Log Analysis & Error Investigation Grafana Dashboard; configure Alertmanager in alertmanager.yml | 3h 30m | Work | Planned | —
13-Aug-2026 | Thursday | 13:00 | 14:00 | Lunch Break | 1h 00m | Break | — | —
13-Aug-2026 | Thursday | 14:00 | 18:00 | Create Webhook Logger service for local alert testing; update README and walkthrough docs | 4h 00m | Work | Planned | —
14-Aug-2026 | Friday | 09:30 | 13:00 | Run full stack sanity test; verify trace-to-log correlation in Grafana | 3h 30m | Work | Planned | —
14-Aug-2026 | Friday | 13:00 | 14:00 | Lunch Break | 1h 00m | Break | — | —
14-Aug-2026 | Friday | 14:00 | 18:00 | Weekly progress summary write-up; prep for Week 7 mentor review | 4h 00m | Work | Planned | —
15-Aug-2026 | Saturday | — | — | Weekend — No Work | — | OFF | — | —
16-Aug-2026 | Sunday | — | — | Weekend — No Work | — | OFF | — | —
WEEK 7 — 17–21 Aug 2026 Phase 1-A Final Sign-Off (20-Aug) & Phase 1-B K8s Start (21-Aug)
17-Aug-2026 | Monday | 09:30 | 13:00 | Demonstrate full monitoring stack to mentor; walkthrough dashboards and alert rules | 3h 30m | [MEETING] | Planned | —
17-Aug-2026 | Monday | 13:00 | 14:00 | Lunch Break | 1h 00m | Break | — | —
17-Aug-2026 | Monday | 14:00 | 18:00 | Note mentor feedback: minor edits to README troubleshooting section | 4h 00m | Work | Planned | —
18-Aug-2026 | Tuesday | 09:30 | 13:00 | Apply mentor feedback to README.md and ARCHITECTURE_EXPLAINED.md | 3h 30m | Work | Planned | —
18-Aug-2026 | Tuesday | 13:00 | 14:00 | Lunch Break | 1h 00m | Break | — | —
18-Aug-2026 | Tuesday | 14:00 | 18:00 | Final verification of all 15 Grafana panels under sustained traffic generator load | 4h 00m | Work | Planned | —
19-Aug-2026 | Wednesday | 09:30 | 13:00 | Clean up scratch files and code comments; push final documentation updates | 3h 30m | Work | Planned | —
19-Aug-2026 | Wednesday | 13:00 | 14:00 | Lunch Break | 1h 00m | Break | — | —
19-Aug-2026 | Wednesday | 14:00 | 18:00 | Prepare Phase 1-A sign-off summary report for mentor | 4h 00m | Work | Planned | —
20-Aug-2026 | Thursday | 09:30 | 13:00 | Phase 1-A Formal Sign-Off Meeting with Senior DevOps Mentor | 3h 30m | [MEETING] | Planned | Phase 1-A monitoring stack formally approved by mentor
20-Aug-2026 | Thursday | 13:00 | 14:00 | Lunch Break | 1h 00m | Break | — | —
20-Aug-2026 | Thursday | 14:00 | 18:00 | Finalize Phase 1-A tracker entries; prep workstation for Kubernetes setup | 4h 00m | Work | Planned | Phase 1-A complete
21-Aug-2026 | Friday | 09:30 | 13:00 | [Phase 1-B Start] Study K8s core concepts: Node, Pod, Container, Namespace | 3h 30m | Study | Planned | —
21-Aug-2026 | Friday | 13:00 | 14:00 | Lunch Break | 1h 00m | Break | — | —
21-Aug-2026 | Friday | 14:00 | 18:00 | Read Kubernetes documentation on Deployment, Service, ConfigMap, and Secret | 4h 00m | Study | Planned | —
22-Aug-2026 | Saturday | — | — | Weekend — No Work | — | OFF | — | —
23-Aug-2026 | Sunday | — | — | Weekend — No Work | — | OFF | — | —

## Weekly Summary
=== WEEK 1 — 10 Jul 2026 (1 Working Day) ===
Working Days | 1 (Friday only)
Total Hours | 7.5h
Phase | Phase 0 — Foundation Setup
Status | Completed
Work Completed / Key Learnings:
* Project kickoff — understood scope, 13 monitoring targets, tech stack
* Installed Java 21, Maven 3.9, IntelliJ IDEA, Postman
* First mvn clean install — 9 minutes; fat JAR created
LEARNING: JAVA_HOME not auto-set after Java 21 install; set manually
CHALLENGES: IntelliJ navigation unfamiliar; JAVA_HOME issue took 30 min
NEXT: Docker Desktop install; run app locally; study Prometheus pull model
=== WEEK 2 — 13–17 Jul 2026 (5 Days) ===
Working Days | 5 (Mon–Fri)
Total Hours | 37.5h
Phase | Phase 1-A — Docker + Observability Stack Setup
Status | Completed
Work Completed / Key Learnings:
* Installed Docker Desktop; resolved WSL2 BIOS Hyper-V issue
* Started Spring Boot locally; tested API via Postman (201 Created for POST /pricing)
* Read PricingController + PricingService; thin controller pattern confirmed
* Studied Prometheus pull model; Grafana datasource concept; observability 3 pillars (metrics/logs/traces)
* Studied Docker networking: containers reach each other by service name not localhost
* Studied OpenTelemetry: spans/traces/OTLP/context propagation; Micrometer Counter/Timer/Gauge
* Studied Loki (log storage) + Tempo (trace storage) role in the Grafana LGTM stack
* Configured management.server.port=8081; exposed health/metrics/prometheus endpoints
* Added micrometer-registry-prometheus; /actuator/prometheus returns 800+ metric lines
* Added Prometheus + Loki + Tempo + Grafana to docker-compose.yml
* Wrote prometheus.yml; fixed scrape target DOWN: port 8080→8081
* Connected all 3 Grafana datasources (Prometheus/Loki/Tempo) via auto-provisioning YAML
LEARNING: Prometheus PULLS; Grafana stores nothing; management port != API port; rate() converts counter to per-second rate
CHALLENGES: Docker WSL2 BIOS issue (1.5h); target DOWN due to wrong port
NEXT: Full dashboard panels — JVM/HTTP/error rate/health; traffic generator
=== WEEK 3 — 20–24 Jul 2026 (5 Days) ===
Working Days | 5 (Mon–Fri)
Total Hours | 37.5h
Phase | Phase 1-A — Full Grafana Dashboard Build
Status | Completed
Work Completed / Key Learnings:
* Created full Grafana dashboard: JVM Heap/NonHeap/GC Pause P99 panels
* Created HTTP request rate, P95 latency, P99 latency, error rate panels
* Created application health Stat panel (up{job=epricing-service})
* Implemented traffic generator shell script (HOME_LOAN/AUTO_LOAN + error scenarios)
* Fixed panel ID conflicts; added row separators; exported dashboard JSON for auto-provisioning
* Tested Prometheus alert rules: inactive→pending→firing transition verified
* Full E2E test: all 6 Docker services started; all 4 scrape targets UP; all 15 panels live
LEARNING: le label mandatory in sum() by() for histogram_quantile; =~5.. regex for all 5xx; alert 'for' clause prevents false positives
CHALLENGES: histogram_quantile NaN (45 min debug); =~5.. vs =500 for error rate
NEXT: Panel polish, PromQL query refinement, documentation guides
=== WEEK 4 — 27–31 Jul 2026 (5 Days) ===
Working Days | 5 (Mon–Fri)
Total Hours | 37.5h
Phase | Phase 1-A — PromQL Refinement & Panel Formatting
Status | Completed
Work Completed / Key Learnings:
* Cleaned up Grafana panel legends (displaying clean names instead of raw PromQL strings)
* Verified error rate panel under simulated 500 error injection from traffic generator
* Organized Grafana dashboard into collapsable row sections (JVM / HTTP / System / Health)
* Verified custom metric labels (product_type=HOME_LOAN/AUTO_LOAN/PERSONAL_LOAN)
* Tested Loki log scraping using app=epricing-service filter
* Verified traceId propagation across Spring Boot logs and Tempo trace spans
LEARNING: Collapsable rows keep Grafana clean; label filtering improves searchability
NEXT: Traffic generator continuous load test & alert rule threshold validation
=== WEEK 5 — 03–07 Aug 2026 (5 Days) ===
Working Days | 5 (Mon–Fri)
Total Hours | 37.5h
Phase | Phase 1-A — Load Testing & Alert Rule Tuning
Status | Completed
Work Completed / Key Learnings:
* Ran 2-hour continuous load test via traffic generator; verified heap auto-reclamation
* Tested Prometheus container restart; verified metric history retention in volume mount
* Tested error injection scenario; verified HighErrorRate alert transition (inactive→pending→firing)
* Added panel descriptions to all 15 Grafana panels via UI edit mode
* Re-exported dashboard JSON to grafana/provisioning/dashboards/ to preserve updates
* Demoed stack to mentor; received feedback to refine alert evaluation window
LEARNING: Docker volume mounts prevent metric loss on container restart; info icons clarify panel purpose
NEXT: Documentation guides & clean workspace build verification
=== WEEK 6 — 10–14 Aug 2026 (5 Days) ===
Working Days | 5 (Mon–Fri)
Total Hours | 37.5h
Phase | Phase 1-A — Documentation & Stack Alignment [CURRENT]
Status | In Progress
Work Completed / Key Learnings:
* Updated docs/README.md with quickstart guide and port reference table
* Tested clean workspace build: docker-compose down -v && docker-compose up --build
* Today (12-Aug): Confirmed stack alignment with mentor; updated timesheet structure
* Foundation marked IN REVISION: Spring Boot internals + Spring Core/DI need revision
* Phase 1-A extended to 20-Aug for final doc polish, mentor review, and clean handover
NEXT: Onboarding setup guide, Loki log search syntax notes, Week 7 mentor sign-off meeting
=== WEEK 7 — 17–21 Aug 2026 (5 Days) ===
Working Days | 5 (Mon–Fri)
Total Hours | 37.5h
Phase | Phase 1-A Sign-Off (20-Aug) + Phase 1-B K8s Start (21-Aug)
Status | Planned
Work Completed / Key Learnings:
* Demonstrate complete LGTM observability stack to Senior DevOps mentor
* Apply final mentor feedback to README.md and ARCHITECTURE_EXPLAINED.md
* Formal Phase 1-A Sign-Off meeting on Thursday 20-Aug-2026
* Friday 21-Aug-2026: Kick off Phase 1-B Kubernetes — read K8s architecture & core concepts
NEXT: Install kubectl + minikube; deploy Hello World pod on 21-Aug
=== OVERALL PROJECT STATUS (as of 12-Aug-2026) ===
Metric | Value | Phase | Progress
Project Start | 10-Jul-2026 | P0 Foundation | In Revision (65%)
Current Date | 12-Aug-2026 | P1-A Observability | In Progress (90%) — Sign-off 20-Aug
P1-A Target End | 20-Aug-2026 | P1-B Kubernetes | Not Started — Kickoff 21-Aug
Working Days Logged | 25 days | P2 Database | Not Started
Total Phases | 6 (P0–P6) | P3 Security | Not Started
Est. Completion | Nov-2026 | P4 CI/CD | Not Started
Confirmed Stack | Grafana·Prometheus·OTel·Loki·Tempo·Dapr·Dynatrace·K8s·PostgreSQL·SonarQube | P5 Obs Scale | Not Started
Project Status | In Progress | P6 K8s Dashboard | Not Started

## LD Tracker
Task ID | Phase | Module | Task Description | Start Date | Target Date | Actual End | Status | Priority | Prerequisites | Progress % | Effort Days | Success Criteria
PHASE 0 — Foundation Revision (Spring Boot Internals · Spring Core/DI) [IN REVISION]
AT-00a | P0 — Foundation | Spring Boot 3 Internals | Revise: @SpringBootApplication, @EnableAutoConfiguration, @Conditional, spring.factories/AutoConfiguration.imports; Bean lifecycle; ApplicationContext vs BeanFactory; @ConfigurationProperties; Spring Profiles; Actuator endpoint internals | 10-Jul-26 | 30-Aug-26 | - | In Revision | High | AT-02 | 40% | 5 | Can trace bean creation in debugger; can explain @Conditional chain for any auto-config; spring.factories mechanism understood
AT-00b | P0 — Foundation | Spring Core — DI & AOP | Revise: @Autowired field/constructor/setter; @Primary vs @Qualifier; circular dependency resolution; @Aspect/@Around/@Before/@After/Pointcut; JDK dynamic proxy vs CGLIB; Spring MVC DispatcherServlet lifecycle; @ControllerAdvice + @ExceptionHandler | 01-Aug-26 | 15-Sep-26 | - | In Revision | High | AT-00a | 25% | 5 | Can write working @Aspect with @Around advice; explain JDK vs CGLIB proxy; DispatcherServlet flow diagram from memory
PHASE 1-A — Core Observability Stack (Prometheus + Grafana + Loki + Tempo + OTel) [IN PROGRESS — Ends 20-Aug]
AT-01 | P1-A | Requirements Analysis | Understand project scope, 13 monitoring targets, deliverables, and confirmed tech stack | 10-Jul-26 | 10-Jul-26 | 10-Jul-26 | Completed | High | None | 100% | 1 | Project kickoff held; 13 metrics documented; tech stack confirmed
AT-02 | P1-A | Environment Setup | Install Java 21, Maven 3.9, Docker Desktop, IntelliJ IDEA, Postman | 10-Jul-26 | 14-Jul-26 | 14-Jul-26 | Completed | High | AT-01 | 100% | 2 | All tools installed; Docker WSL2 BIOS issue resolved
AT-03 | P1-A | Observability Architecture Study | Study Prometheus pull model, Grafana, Micrometer, OpenTelemetry, Loki, Tempo, observability 3 pillars | 11-Jul-26 | 17-Jul-26 | 17-Jul-26 | Completed | High | AT-01 | 100% | 3 | Architecture notes complete; metrics vs logs vs traces understood; LGTM stack flow documented
AT-04 | P1-A | Spring Boot Actuator | Configure management port 8081; expose /actuator/health, /actuator/prometheus endpoints | 17-Jul-26 | 17-Jul-26 | 17-Jul-26 | Completed | High | AT-02,AT-03 | 100% | 1 | /actuator/prometheus returning Prometheus text format on port 8081
AT-05 | P1-A | Micrometer Integration | Add micrometer-registry-prometheus; verify pricing_requests_total counter + Timer in /actuator/prometheus | 17-Jul-26 | 20-Jul-26 | 20-Jul-26 | Completed | High | AT-04 | 100% | 1 | pricing_requests_total{product_type,status} labels visible; Counter increments per API call
AT-06 | P1-A | Prometheus + Grafana + Loki + Tempo Setup | Write prometheus.yml; add all 4 services to docker-compose.yml; connect all 3 Grafana datasources via provisioning YAML | 20-Jul-26 | 24-Jul-26 | 24-Jul-26 | Completed | High | AT-05 | 100% | 3 | All 4 scrape targets UP; Loki/Tempo/Prometheus datasources auto-loaded in Grafana
AT-07 | P1-A | PromQL Study + Dashboard Panels | Study rate()/histogram_quantile()/sum() by(); create JVM/HTTP/error rate/health panels | 24-Jul-26 | 31-Jul-26 | 31-Jul-26 | Completed | Medium | AT-06 | 100% | 4 | 15 panels; le label requirement understood; error rate formula: sum(rate({status=~5..}[5m]))/total*100
AT-08 | P1-A | Traffic Generator | Implement shell script: HOME_LOAN/AUTO_LOAN/PERSONAL_LOAN + error + slow request scenarios | 24-Jul-26 | 31-Jul-26 | 31-Jul-26 | Completed | Medium | AT-04 | 100% | 1 | All 15 panels live with traffic generator running
AT-09 | P1-A | Dashboard Improvements | Fix panel ID conflicts; add row sections; add descriptions; export JSON for provisioning | 31-Jul-26 | 06-Aug-26 | 06-Aug-26 | Completed | Medium | AT-07,AT-08 | 100% | 1 | Dashboard auto-loads on docker-compose up; all panels described
AT-10 | P1-A | Testing & Validation | E2E test: all 6 Docker services; all 4 scrape targets UP; all 15 panels under load; alert rules inactive→pending→firing | 05-Aug-26 | 08-Aug-26 | 08-Aug-26 | Completed | High | AT-09 | 100% | 2 | All 15 panels verified; alert rule transitions confirmed
AT-11 | P1-A | Documentation & Sign-Off | Write README, ARCHITECTURE_EXPLAINED.md, SIMPLE_OBSERVABILITY_GUIDE.md; mentor demo & sign-off | 08-Aug-26 | 20-Aug-26 | - | In Progress | Medium | AT-10 | 75% | 5 | README + architecture docs drafted; Log Analysis Dashboard & Alertmanager added; sign-off target 20-Aug
PHASE 1-B — Kubernetes Fundamentals [NOT STARTED — Starts 21-Aug]
LD-01 | P1-B — K8s | K8s Core Concepts | Study: Node, Pod, Deployment, Service, ConfigMap, Secret, Namespace hierarchy | 21-Aug-26 | 24-Aug-26 | - | Not Started | High | Docker knowledge | 0% | 1 | Can explain Node→Pod→Container; can draw K8s architecture from memory
LD-02 | P1-B — K8s | Local K8s Setup | Install kubectl + minikube; deploy Hello World pod; kubectl get pods shows Running | 24-Aug-26 | 26-Aug-26 | - | Not Started | High | LD-01 | 0% | 1 | kubectl get nodes Ready; Hello World pod Running
LD-03 | P1-B — K8s | Namespace + RBAC | Create epricing namespace; apply ServiceAccount + Role; verify cross-namespace access denied | 26-Aug-26 | 28-Aug-26 | - | Not Started | High | LD-02 | 0% | 1 | kubectl get pods -n epricing works; cross-namespace denied
LD-04 | P1-B — K8s | ConfigMap + Secret | Write ConfigMap (SPRING_PROFILES_ACTIVE) + Secret (DB creds); verify env var injection in pod | 28-Aug-26 | 31-Aug-26 | - | Not Started | High | LD-03 | 0% | 1 | kubectl describe pod shows env vars from ConfigMap+Secret
LD-05 | P1-B — K8s | epricing Deployment | Write Deployment manifest (replicas:3) with liveness probe (/actuator/health) + readiness probe | 31-Aug-26 | 03-Sep-26 | - | Not Started | High | LD-04 | 0% | 2 | 3 pods Running; kubectl rollout status complete; probes configured
LD-06 | P1-B — K8s | K8s Service + Ingress | Write ClusterIP Service; configure Nginx Ingress exposing /api/v1; test with curl | 03-Sep-26 | 05-Sep-26 | - | Not Started | High | LD-05 | 0% | 1 | curl http://epricing.local/api/v1/health returns 200 OK
LD-07 | P1-B — K8s | Horizontal Pod Autoscaler | Configure HPA (min:2 max:10 CPU>70%); run load test; observe pod scale-up | 07-Sep-26 | 09-Sep-26 | - | Not Started | Medium | LD-05 | 0% | 1 | kubectl get hpa shows CPU Targets increasing; pod count scales under load
LD-08 | P1-B — K8s | Resource Requests + Limits | Set requests (256Mi/250m) and limits (512Mi/1000m) on all pods | 09-Sep-26 | 11-Sep-26 | - | Not Started | Medium | LD-05 | 0% | 1 | kubectl describe pod shows resources; OOMKilled does not occur under normal load
PHASE 2 — Production Database (PostgreSQL + Flyway on Kubernetes)
LD-09 | P2 — Database | PostgreSQL StatefulSet | Deploy PostgreSQL 16 StatefulSet with PVC in K8s; connect psql CLI; verify data survives Pod restart | 14-Sep-26 | 17-Sep-26 | - | Not Started | High | LD-03 | 0% | 2 | psql connects; data survives Pod restart
LD-10 | P2 — Database | Spring Boot PostgreSQL Config | Add PostgreSQL datasource to application.yml (prod profile); remove H2 dependency; verify db UP | 17-Sep-26 | 19-Sep-26 | - | Not Started | High | LD-09 | 0% | 1 | /actuator/health shows db UP; POST /pricing saves to PostgreSQL
LD-11 | P2 — Database | Flyway Migration | Write V1__init.sql; add Flyway to pom.xml; verify migration on startup | 21-Sep-26 | 23-Sep-26 | - | Not Started | High | LD-10 | 0% | 1 | Flyway: Successfully applied 1 migration in startup logs
LD-12 | P2 — Database | DB Backup Strategy | Document pg_dump cron job backup; test restore in dev environment | 23-Sep-26 | 25-Sep-26 | - | Not Started | Medium | LD-09 | 0% | 1 | pg_dump generates .sql backup; restore works in test environment
PHASE 3 — Enterprise Security (JWT + K8s Secrets + HTTPS + AuditLog)
LD-13 | P3 — Security | JWT Authentication | Add Spring Security 6 + oauth2-resource-server; protect /api/v1/pricing with JWT Bearer token | 28-Sep-26 | 30-Sep-26 | - | Not Started | High | LD-06 | 0% | 2 | 401 without JWT; 200 OK with valid signed JWT
LD-14 | P3 — Security | K8s Secrets Management | Move DB credentials to K8s Secrets; no plaintext passwords in any config file | 30-Sep-26 | 02-Oct-26 | - | Not Started | High | LD-04 | 0% | 1 | kubectl get secret shows credentials; no plaintext in YAML or application.yml
LD-15 | P3 — Security | HTTPS / TLS on Ingress | Configure Ingress TLS with self-signed certificate; HTTP redirects to HTTPS | 02-Oct-26 | 05-Oct-26 | - | Not Started | High | LD-06 | 0% | 1 | curl https://epricing.local returns 200; HTTP redirects to HTTPS
LD-16 | P3 — Security | Non-Root Container + Network Policy | Add runAsNonRoot:true securityContext; write NetworkPolicy allowing only Prometheus to scrape :8081 | 05-Oct-26 | 07-Oct-26 | - | Not Started | Medium | LD-05 | 0% | 1 | whoami in pod = non-root; curl from traffic-generator to :8081 refused
LD-17 | P3 — Security | @AuditLog AOP Interceptor | Implement @AuditLog AOP interceptor writing customerId + endpoint + timestamp to audit_log table | 07-Oct-26 | 09-Oct-26 | - | Not Started | High | LD-10 | 0% | 2 | Every POST /pricing creates audit_log row; AOP proxy verified in logs
PHASE 4 — CI/CD Pipeline (GitHub Actions + SonarQube + Kubernetes Deploy)
LD-18 | P4 — CI/CD | GitHub Actions Setup | Create .github/workflows/ci.yml; run mvn clean test on push to main; GitHub Actions badge green | 12-Oct-26 | 14-Oct-26 | - | Not Started | High | Git repo setup | 0% | 1 | GitHub Actions badge green on README
LD-19 | P4 — CI/CD | Docker Build + Registry Push | Build Docker image in pipeline; push to container registry with git SHA tag | 14-Oct-26 | 16-Oct-26 | - | Not Started | High | LD-18 | 0% | 1 | Image pushed to registry with git SHA tag after each successful pipeline run
LD-20 | P4 — CI/CD | Automated K8s Deploy | Add kubectl rollout step to update Deployment image to new tag in K8s | 16-Oct-26 | 19-Oct-26 | - | Not Started | High | LD-19 | 0% | 1 | Push to main → pipeline → K8s pods restart with new image within 3 minutes
LD-21 | P4 — CI/CD | SonarQube Quality Gate | Deploy SonarQube on K8s / SonarCloud; add sonar-maven-plugin; configure Bugs/Vulnerabilities/Hotspots rules; block PR merge on FAILED Quality Gate | 19-Oct-26 | 21-Oct-26 | - | Not Started | High | LD-18 | 0% | 2 | Quality Gate PASSED on main; 0 Bugs and 0 Vulnerabilities; PR blocked on FAILED gate
LD-22 | P4 — CI/CD | Staging vs Production Pipelines | Auto-deploy to staging on main push; manual approval gate for production via GitHub Environments | 21-Oct-26 | 23-Oct-26 | - | Not Started | High | LD-20 | 0% | 2 | Staging auto-deploys; production deploy waits for GitHub Environment approval
PHASE 5 — Observability Scale-Up (K8s SD + Grafana Alerting + OTel Sampling + Dynatrace)
LD-23 | P5 — Obs Scale | Prometheus K8s Service Discovery | Configure kubernetes_sd_configs to scrape pods by label selector instead of static IPs | 26-Oct-26 | 28-Oct-26 | - | Not Started | High | LD-05 | 0% | 1 | Prometheus Targets shows epricing pods discovered dynamically by label
LD-24 | P5 — Obs Scale | Grafana Alerting Rules | Configure Grafana built-in alerting: ErrorRate>5% for 2 min → notification channel (email/webhook); Loki retention 720h | 28-Oct-26 | 30-Oct-26 | - | Not Started | High | Grafana running | 0% | 1 | Alert fires and notification sent when error rate threshold breached; Loki logs from 8 days ago queryable
LD-25 | P5 — Obs Scale | OTel Sampling Strategy | Change OTel sampler to parentbased_traceidratio ratio=0.1 for high-traffic endpoints; validate no P95 latency degradation | 02-Nov-26 | 04-Nov-26 | - | Not Started | Medium | OTel Collector | 0% | 1 | ~10% traces in Tempo; no latency degradation
LD-26 | P5 — Obs Scale | Dynatrace OTLP Integration | Configure OTel Collector to dual-export traces+metrics: Tempo (internal) + Dynatrace OTLP endpoint; review Davis AI topology map; add Dapr tracing to Grafana dashboard | 04-Nov-26 | 06-Nov-26 | - | Not Started | High | Dynatrace account + OTel running | 0% | 2 | Same traceId visible in both Tempo and Dynatrace; Davis AI auto-discovers epricing service topology; Dapr sidecar spans visible
PHASE 6 — K8s Infrastructure Utilization Dashboard (Container / Node / Pod)
LD-27 | P6 — K8s Dash | Node Exporter DaemonSet | Deploy Prometheus Node Exporter DaemonSet to collect host CPU/RAM/disk/network metrics per Node | 09-Nov-26 | 11-Nov-26 | - | Not Started | High | LD-05 | 0% | 1 | node_cpu_seconds_total appears per node; DaemonSet on every node
LD-28 | P6 — K8s Dash | kube-state-metrics | Deploy kube-state-metrics; expose Pod phase, HPA replicas, Deployment readiness, resource requests/limits to Prometheus | 11-Nov-26 | 13-Nov-26 | - | Not Started | High | LD-05 | 0% | 1 | kube_pod_container_resource_requests visible in Prometheus
LD-29 | P6 — K8s Dash | Container Utilization Dashboard | Grafana panels: Container CPU % (container_cpu_usage_seconds_total); Container Memory vs limit; Container restart count | 13-Nov-26 | 16-Nov-26 | - | Not Started | High | LD-27,LD-28 | 0% | 2 | Per-container CPU/RAM live; restart spikes visible for OOMKilled/crash-loop containers
LD-30 | P6 — K8s Dash | Node Utilization Dashboard | Grafana panels: Node CPU % (1 - avg(rate(node_cpu_seconds_total{mode=idle}[5m])) by instance); Node Memory available; Node Disk I/O; Node Network bytes | 16-Nov-26 | 18-Nov-26 | - | Not Started | High | LD-27 | 0% | 2 | Node saturation visible before Pods fail; helps plan cluster scale-out
LD-31 | P6 — K8s Dash | Pod + HPA + Deployment Dashboard | Grafana panels: Pod CPU/RAM per namespace; HPA desired vs current replicas; Deployment ready vs desired; Pod phase distribution (Running/Pending/Failed) | 18-Nov-26 | 20-Nov-26 | - | Not Started | High | LD-27,LD-28,LD-07 | 0% | 2 | HPA scale events visible; Deployment health at a glance; Pod phases breakdown
LD-32 | P6 — K8s Dash | Dapr Observability in Grafana | Configure Dapr metrics scraping in Prometheus; add Dapr dashboard in Grafana showing service-to-service call latency and success rate; correlate Dapr traces in Tempo + Dynatrace | 20-Nov-26 | 23-Nov-26 | - | Not Started | Medium | Dapr + OTel running | 0% | 2 | Dapr service call latency visible in Grafana; traceId from Dapr spans appears in both Tempo and Dynatrace

## Tech Stack Reference
CONFIRMED TECH STACK REFERENCE — ePricing Service
Category | Technology | Role in Enterprise Stack | How it Fits in ePricing | Phase
App Runtime | Spring Boot 3.3 | Microservice framework; auto-configuration, DI, embedded Tomcat, Actuator | Core application: pricing API (/api/v1/pricing), health endpoints, metrics exposure via Actuator | P0, All
App Runtime | Java 21 LTS | Programming language; Virtual Threads (Project Loom) for high concurrency | JVM runtime; virtual threads reduce thread pool overhead for concurrent pricing requests | P0, All
App Runtime | Maven | Build tool; dependency management, lifecycle (clean/compile/test/package) | mvn clean install builds fat JAR; mvn clean test runs unit tests in CI/CD pipeline | P0, P4
App Runtime | Docker | Container build and runtime; Docker Compose for local multi-service orchestration | Builds epricing-service image; Docker Compose runs Prometheus+Grafana+Loki+Tempo locally for dev/test | P0, P1-A
Microservice Runtime | Dapr | Microservice building blocks: service invocation, pub/sub, state mgmt, secrets — sidecar pattern | Auto-propagates OTel trace headers (traceparent) between microservices; Dapr metrics + traces flow to Prometheus + Tempo + Dynatrace | P5, P6
Observability — Metrics | Micrometer | Vendor-neutral metrics facade for Spring Boot; auto-instruments JVM, HTTP server, custom metrics | Exposes pricing_requests_total (Counter) + pricing_duration (Timer) on /actuator/prometheus; feeds Prometheus | P1-A
Observability — Metrics | Prometheus | Time-series database with pull-based scraping; stores numeric metrics over time; PromQL query language | Scrapes /actuator/prometheus every 15s; stores CPU, RAM, HTTP latency, pricing request count metrics; K8s SD for pod auto-discovery | P1-A, P5
Observability — Logs | Grafana Loki | Log aggregation system; indexes labels not full text; stores all application log streams | Stores epricing-service JSON logs; queryable by traceId, customerId, log level; linked from Grafana panels | P1-A, P5
Observability — Traces | OpenTelemetry (OTel) | Vendor-neutral observability standard: SDKs + Collector pipeline for Traces, Metrics, Logs | Auto-instruments HTTP spans; attaches traceId to every request; OTel Collector routes to Tempo (internal) + Dynatrace (enterprise) | P1-A, P5
Observability — Traces | Grafana Tempo | High-scale distributed trace storage backend; stores full request span trees | Stores all OTel traces from Collector; traces clickable from Grafana Loki logs via traceId correlation (trace-to-log linking) | P1-A
Observability — APM | Dynatrace | Enterprise APM + AI Ops: Davis AI for automated root cause analysis, full-stack topology mapping, synthetic monitoring | Receives OTel metrics + traces via OTLP endpoint (dual-shipping from OTel Collector); Davis AI auto-discovers epricing service dependencies; unified enterprise view alongside Grafana | P5
Visualization | Grafana | Unified dashboard + alerting platform; queries Prometheus, Loki, Tempo simultaneously | Central observability UI: JVM panels, HTTP panels, K8s Container/Node/Pod panels, alert rules, Loki log explore, Tempo trace drill-down | P1-A, P5, P6
Container Orchestration | Kubernetes (K8s) | Container orchestration: Node/Pod/Deployment/Service/ConfigMap/Secret/HPA/NetworkPolicy/Ingress | Runs epricing-service Deployment (replicas:3); manages HPA auto-scaling, Secrets, Ingress routing, resource limits | P1-B+
Container Orchestration | kubectl | CLI to interact with Kubernetes API server: apply/get/describe/delete K8s resources | All K8s management: kubectl apply -f, get pods, describe pod, rollout status, get hpa | P1-B+
Database | PostgreSQL 16 | Production-grade relational database; ACID compliance; K8s StatefulSet with PVC for persistence | Replaces H2 in-memory DB for production; stores pricing_requests table; StatefulSet gives stable Pod identity; PVC preserves data across restarts | P2
Database | H2 (Dev only) | In-memory embedded database for local development and testing only | Used only for local Spring Boot dev run (dev profile); removed when switching to PostgreSQL (prod profile) | P0, P1-A
Database Migration | Flyway | Database schema versioning; SQL migration scripts applied automatically on Spring Boot startup | Runs V1__init.sql to create pricing_requests table on first startup; ensures schema consistency across all environments | P2
Security | Spring Security 6 + OAuth2 | Authentication + authorization framework; JWT Bearer token validation as resource server | Protects /api/v1/pricing endpoint; returns 401 Unauthorized without valid JWT; internal services trusted within K8s namespace | P3
CI/CD | GitHub Actions | Cloud-based CI/CD automation; YAML workflow files triggered on git events | ci.yml: runs mvn clean test → Docker build → registry push → kubectl rollout on push to main; GitHub Environments for manual production gate | P4
CI/CD | SonarQube | Enterprise static code analysis: detects Bugs, Vulnerabilities, Code Smells, Security Hotspots; Quality Gate as pipeline blocker | Deployed on K8s or SonarCloud SaaS; sonar-maven-plugin in pom.xml; Quality Gate FAILED blocks PR merge; Security Hotspot dashboard for mentor review | P4